## PMP
Project Management Plan
Communication via Microsoft Teams
Day of the Week: | Tasks: | Assigned To: | Aim Date: | Date Completed: | Estimated Time:
Friday (5/6) | Begin Search for Datasets | Group | (5/6) | (5/6) | 3 HRS
| Discuss Datasets and Evaluate | Group | (5/6) | (5/6) | 1 HR
| Develop Elevator Pitch | Group | (5/6) | (5/6) | 30 MIN
Monday (5/9) | Present Elevator Pitch | Group | (5/9) | (5/9) | 30 MIN
| Incorporate Instructors Feedback | Group | (5/9) | (5/9) | 30 MIN
| Initial Question Ideas | Group | (5/9) | (5/9) | 2 HRS
Tuesday (5/10) | Brainstrom Visualization Ideas for Napkin Drawings | Group | (5/10) | (5/10) | 1 HR
| Visualizations Napkin Drawings | Isaac | (5/10) | (5/10) | 1 HR
| Begin Data Extraction web-scraping | Yansong | (5/10) | (5/10) | 3 HRS
| Begin Data Cleaning | Yansong | (5/10) | (5/10) | 1 HR
| Question Review with Instructors | Group | (5/10) | (5/10) | 15 MIN
Wednesday (5/11) | Discuss ML Model and Ideas | Group | (5/11) | (5/11) | 1 HR
| Finalize Decision about what ML Model to use | Group | (5/11) | (5/11) | 2 HRS
| Begin setting up Project Management Plan | Alex | (5/11) | (5/11) | 2 HRS
| Discuss PMP Dates | Group | (5/11) | (5/11) | 2 HRS
| Create and Populate Databases from Kafka Messages | Yansong | (5/11) | (5/11) | 2 HRS
| Get Census Data from API Call | Will | (5/12) | (5/11) | 2 HRS
Thurday (5/12) | Receive Feedback on Visualization ND | Isaac, Yansong | (5/12) | (5/12) | 30 MIN
| Update Feedback Visualization ND | Isaac | (5/12) | (5/12) | 30 MIN
| ETL for Census Data | Will | (5/12) | (5/12) | 2 HRS
| Create Test Visualization in PowerBI | Isaac | (5/12) | (5/12) | 2 HRS
| Discuss Test Visualizations in PowerBI | Group | (5/12) | (5/12) | 1 HR
| Begin Prototype ML Model | Will | (5/12) | (5/12) | 3 HRS
| Start Automatic Web Scraping and Kafka Dataflow | Yansong | (5/12) | (5/12) | 3 HRS
| Continue Working on PMP | Alex | (5/12) | (5/12) | 2.5 HRS
Friday (5/13) | Refine ML Model | Will | (5/13) |  | 2 HRS
| Finalize PMP | Alex | (5/13) |  | 2 HRS
| Discuss Data Platform Diagram | Group | (5/13) |  | 30 MIN
| Create Data Platform Diagram | Yansong | (5/13) |  | 2 HRS
| Create Data Source Document | Isaac | (5/13) |  | 2 HRS
| Discuss Group Findings | Group | (5/13) |  | 2 HRS
| Executive Summary | Alex | (5/13) |  | 1 HR
| Formal Kickoff with Instructors | Group | (5/13) |  | 30 MIN
Weekend (5/14 - 5/15) | Begin work on ETL Report | Group | (5/15) |  | 2 HRS
| Begin ERD | Group | (5/15) |  | 2 HRS
| Fix Paths for Dataflow Accordingly | Yansong | (5/15) |  | 2 HRS
| Finish ERD | Group | (5/15) |  | 1 HR
| Wrap-up Unfinished Tasks | Group | (5/15) |  | 2 HRS
Monday (5/16) | Discuss ERD | Group | (5/16) |  | 15 MIN
| Ideas for Report Format | Group | (5/16) |  | 2 HRS
| Create Napkin Drawings for Report | Isaac | (5/16) |  | 2 HRS
| Receive Feedback for Report ND | Isaac, Yansong | (5/16) |  | 30 MIN
| Update ND based on Feedback | Isaac | (5/16) |  | 1 HR
| Add Project and Data Sources in ETL Report | Isaac, Alex | (5/16) |  | 2 HRS
| Describe Data Source in ETL Report | Will, Yansong | (5/16) |  | 3 HRS
Tuesday (5/17) | Import Code Snippets to ETL Report | Isaac, Alex | (5/17) |  | 2 HRS
| Explain Code Snippets | Isaac, Alex | (5/17) |  | 2 HRS
| Finalize Visualizations | Group | (5/17) |  | 2 HRS
| Discuss Visualizations | Group | (5/17) |  | 2 HRS
| Discuss Technical Report | Group | (5/17) |  | 1 HR
Wednesday (5/18) | Continue Work on ETL Report | Group | (5/18) |  | 2 HRS
| Repeat ETL Process | Group | (5/18) |  | 1 HR
| Discuss ETL Report | Group | (5/18) |  | 30 MIN
| Adjust ETL Report | Group | (5/18) |  | 1 HR
| Finalize ETL Report | Group | (5/18) |  | 1 HR
| Begin Technical Report Rough Draft | Group | (5/18) |  | 30 MIN
Thursday (5/19) | Draft Backstory for Technical Report | Group | (5/19) |  | 2 HRS
| Discuss Backstory Technical Report | Group | (5/19) |  | 2 HRS
| Finalize Backstory | Group | (5/19) |  | 3 HRS
| Discuss Research within Technical Report | Group | (5/19) |  | 2 HRS
Friday (5/20) | Work on Technical Report Research Section | Group | (5/20) |  | 3 HRS
| Finalize Research Section | Group | (5/20) |  | 2 HRS
| Begin Adding Snippets to Technical Report | Group | (5/20) |  | 2 HRS
Weekend (5/21 - 5/22) | Catch-up/ Finalize Technical Report | Group | (5/22) |  | 4 HRS
Monday (5/23) | Create Basis of Presentation Slides and Organization | Group | (5/23) |  | 2 HRS
| Populate Presentation Slides with Text | Group | (5/23) |  | 2 HRS
| Populate Presentation Slides with Visuals | Group | (5/23) |  | 2 HRS
| Collect Thoughts and Ideas for Presentation | Group | (5/23) |  | 2 HRS
Tuesday (5/24) | Adjustments to Presentation slides | Group | (5/24) |  | 2 HRS
| Final Check on ML Model, Visualizations, etc. | Group | (5/24) |  | 2 HRS
| Discuss Any additional Information | Group | (5/24) |  | 2 HRS
Wednesday (5/25) | Finalize Presentation Slides | Group | (5/25) |  | 2 HRS
| Practice Slides | Group | (5/25) |  | 2 HRS
| Check Rubric and Compare | Group | (5/25) |  | 2 HRS
| Additional Time for Adjustments | Group | (5/25) |  | 2 HRS
Thursday (5/26) | Presentation to Class | Group | (5/26) |  | 30 MIN
| Take in Feedback | Group | (5/26) |  | 30 MIN
| Incorporate Feedback into Presentation | Group | (5/26) |  | 1 - 2 HRS
| Practice Slides | Group | (5/26) |  | 2 HRS
Friday (5/27) | Presentation to All | Group | (5/27) |  | 30 MIN